## Currently Certified Projects
2016 List of FCM Certified Transmission Projects
(intended for all network model builds in year 2016, including FCA #11 - CCP 2020-21)
State | Projected In Service Date (RSP Date)* | Major Project | Project Component | RSP Project Number | PPA (I.3.9) Approval | TCA Approval | Responsible TO | FCM Certified In-Service Date
CT | 2015-12-01 | NEEWS (Interstate Reliability Project) | Build new 345 kV Line 341, Lake Road - CT/RI border West Farnum | 191 | 9/24/2008 5/4/2012 | No | Eversource | 2015-12-01
CT | 2015-12-01 | NEEWS | Sag elimination on 1410 Line (Montville-Buddington) | 1245 | 2011-06-09 | No | CMEEC | 2014-04-01
CT | 2017-12-01 | SWCT | Baird 115/13.8 kV Substation Rebuild (formerly known as Baird 115 kV Bus Upgrade) | 1381 | 8/27/2012 9/9/14 | No | UI | 2018-03-01
CT | 2016-12-01 | SWCT | North Haven to Walrec 1630-3 115 kV relay upgrade (formerly known as North Haven to Walrec 1630-3 line & relay upgrade) | 1383 | 2012-08-27 | NR | UI | 2016-12-01
CT | 2016-12-01 | SWCT | Milvon to Devon Tie 88005A - 89005B 115 kV Line Upgrade | 1384 | 2012-08-27 | 2015-04-17 | UI | 2016-12-01
CT | 2016-03-01 | SWCT | Hawthorne 115 kV Capacitor Bank Addition | 1389 | 10/5/2012 02/27/2014 | No | UI | 2016-03-01
CT | 2015-12-01 | SWCT | East Devon 345 kV voltage 11T Series Breaker addition | 1399 | 2015-04-16 | NR | Eversource | 2015-12-01
CT | 2017-06-01 | Cos Cob Breaker Addition | Add a new 115 kV circuit breaker at the COS COB Substation and reposition 1750 line termination to accommodate Greenwich area Substation | 1533 | 2/11/2014 5/1/2015 | No | Eversource | 2017-06-01
CT | 2015-12-01 | SWCT | Upgrade 1876 line terminal equipment at Newtown Substation | 1566 | NR | No | Eversource | 2015-12-01
CT | 2017-12-01 | SWCT | Reconductor the 1575 Line (Bunker Hill – Baldwin Junction; 3.0 miles) | 1575 | 2015-04-16 | No | Eversource | 2018-06-01
CT | 2016-01-01 | GHCC | Add a new 345/115 kV autotransformer at Barbour Hill and associated terminal equipment | 1580 | 2015-04-16 | No | Eversource | 2016-12-01
CT | 2016-12-01 | GHCC | Reconductor the 115 kV line between Manchester and Barbour Hill (1763) – 7.6 miles | 1581 | 2015-04-16 | No | Eversource | 2016-12-01
CT | 2016-01-01 | GHCC | Add a 345 kV breaker in series with breaker 24T at the Manchester 345 kV switchyard | 1582 | 2015-04-16 | No | Eversource | 2016-12-01
CT | 2018-12-01 | GHCC | Add a new 10.35 mile, 115 kV line from Frost Bridge to Campville and associated terminal equipment | 1583 | 2015-04-16 | No | Eversource | 2018-06-01
CT | 2018-12-01 | GHCC | Separation of 115 kV DCT corresponding to the Frost Bridge to Campville (1191) line and the Thomaston to Campville (1921) line and add a breaker at Campville 115 kV substation | 1584 | 2015-04-16 | No | Eversource | 2018-12-01
CT | 2017-12-01 | GHCC | Upgrade terminal equipment on the 115 kV line between Chippen Hill and Lake Avenue Junction (1810-3). Reconductor the 115 kV line between Southington and Lake Avenue Junction (1810-1) – 5.2 miles | 1585 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2017-12-01 | GHCC | Replace the existing 3% series reactors on the 115 kV lines between Southington and Todd (1910) and between Southington and Canal (1950) with 5% series reactors | 1586 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2017-12-01 | GHCC | Replace the normally open 19T breaker at Southington with a 3% series reactor between Southington Ring 1 and Southington Ring 2 and associated substation upgrades | 1587 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2017-12-01 | GHCC | Add a breaker in series with breaker 5T at the Southington 345 kV switchyard | 1588 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2018-12-01 | GHCC | Add a new 4 mile 115 kV underground cable from Newington to Southwest Hartford and associated terminal equipment including a 2% series reactor | 1590 | 2015-04-16 | No | Eversource | 2018-12-01
CT | 2017-12-01 | GHCC | Loop the 1779 line between South Meadow and Bloomfield into the Rood Avenue substation and reconfigure the Rood Avenue substation | 1591 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2018-12-01 | GHCC | Reconfigure the Berlin 115 kV substation including the addition of two 115 kV breakers and the relocation of a capacitor bank | 1592 | 2015-04-16 | No | Eversource | 2018-12-01
CT | 2016-12-01 | GHCC | Add a 115 kV 25.2 MVAR capacitor at Westside 115 kV substation | 1593 | 2015-04-16 | No | Eversource | 2016-12-01
CT | 2018-12-01 | GHCC | Reconductor the 115 kV line between Newington and Newington Tap (1783) - 0.01 mile | 1594 | 2015-04-16 | No | Eversource | 2018-12-01
CT | 2017-12-01 | GHCC | Separation of 115 kV DCT corresponding to the Bloomfield to South Meadow (1779) line and the Bloomfield to North Bloomfield (1777) line and add a breaker at Bloomfield 115 kV substation | 1595 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2018-12-01 | GHCC | Install a 115 kV 3% series reactor on the underground cable between South Meadow and Southwest Hartford (1704) | 1596 | 2015-04-16 | No | Eversource | 2018-12-01
CT | 2017-12-01 | GHCC | Separation of 115 kV DCT corresponding to the Bloomfield to North Bloomfield (1777) line and the North Bloomfield – Rood Avenue – Northwest Hartford (1751) line and add a breaker at North Bloomfield 115 kV substation | 1597 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2016-12-01 | GHCC | Add a 2nd 345/115 kV autotransformer at Haddam substation and reconfigure the 3-terminal 345 kV 348 line into 2 two-terminal lines | 1598 | 2015-04-16 | No | Eversource | 2016-12-01
CT | 2017-12-01 | GHCC | Separation of 115 kV double circuit towers corresponding to the Branford – Branford RR line (1537) and the Branford to North Haven (1655) line and adding a series breaker at Branford 115 kV substation | 1600 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2017-12-01 | GHCC | Redesign the Green Hill 115 kV substation from a straight bus to a ring bus and add a 37.8 MVAR capacitor bank | 1603 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2016-12-01 | GHCC | Add a 37.8 MVAR capacitor bank at Hopewell 115 kV substation | 1604 | 2015-04-16 | No | Eversource | 2016-03-01
CT | 2017-12-01 | GHCC | Separation of 115 kV double circuit towers corresponding to the Middletown – Pratt and Whitney line (1572) and the Middletown to Haddam (1620) line | 1605 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2017-12-01 |  | 1779 Line Partial Rebuild | 1606 | 2015-04-16 | No | Eversource | 2017-12-01
CT | 2015-12-01 | Asset Replacement | Replace both 345/115 kV Montville autotransformers | 1607 | 2014-08-08 | No | Eversource | 2017-05-01
CT | 2017-12-01 | GHCC | Increase the size of the existing 115 kV capacitor at Branford substation from 37.8 to 50.4 MVAR | 1659 | 2015-04-16 | No | Eversource | 2017-12-01
MA | 2015-12-01 | NEEWS (Interstate Reliability Project)** | New 345 kV (366) line Millbury to MA/RI state line | 190 | 9/24/2008 5/4/2012 | No | NGRID | 2015-12-01
MA | 2016-06-01 |  | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | 782 | 2014-02-11 | No | NGRID | 2016-06-01
MA | 2017-05-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Bear Swamp - install one 230-115 kV 333 MVA auto transformer, one 115 kV breaker, four 230 kV breaker replacements and upgrade various terminal equipment. | 937 | 12/17/2007 | No | NGRID | 2017-05-01
MA | 2017-03-01 | Central/Western Massachusetts Upgrades - Group 6 - Miscellaneous Western Ma Projects | Adams - install two new 115 kV breakers and replace two existing 115 kV breakers and associated line relocations | 945 | 12/17/2007 12/7/2012 | No | NGRID | 2017-05-01
MA | 2015-12-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | 946 | 2011-03-29 | No | NGRID | 2016-06-01
MA | 2017-07-01 | Greater Boston - South*** | Add third 115kV line from W. Walpole to Holbrook | 965 | No | No | Eversource | 2017-07-01
MA | 2015-12-01 | NEEWS (Interstate Reliability Project)** | Upgrade and expand the 345kV Millbury Substation equipment | 1094 | 9/24/2008 5/4/2012 | No | NGRID | 2015-12-01
MA | 2016-12-01 | Greater Boston - Western Suburbs *** | Install a new 230/115 kV auto-transformer at Sudbury Loop 230 kV line 282-602 in and out of a new 230 kV switchyard at Sudbury | 1199 | 2015-07-23 | No | Eversource | 2016-12-01
MA | 2017-06-01 | Greater Boston - North*** | 115 kV Line Reconductoring of M-139 between Tewksbury-Billerica Tap and associated work at Tewksbury | 1212 | 2015-05-01 | No | NGRID | 2017-05-01
MA | 2017-12-01 | Greater Boston - North*** | Install new 345 kV (3124) circuit betweenNH/MA border and Tewksbury (this is the MA portion of NGRID's portion of the new Scobie-Tewksbury circuit) and associated substation work at Tewksbury | 1213 | No | No | NGRID | 2017-12-01
MA | 2016-12-01 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115 kV autotransformer | 1221 | 2012-12-07 | No | Eversource | 2016-12-01
MA | 2016-12-01 | Pittsfield / Greenfield Project | Build a new 115 kV three breaker Switching Station (Erving) ring bus | 1222 | 2012-12-07 | No | Eversource | 2016-12-01
MA | 2016-12-01 | Pittsfield / Greenfield Project | Build a new 115 kV line from Northfield Mountain to the new Erving Switching Station | 1223 | 2012-12-07 | No | Eversource | 2016-12-01
MA | 2016-02-01 | Pittsfield / Greenfield Project | Install 115 kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations | 1224 | 2012-12-07 | No | Eversource | 2016-12-01
MA | 2015-12-01 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361 115 kV line and terminal work at Cumberland and Montague. At Montague substation, reconnect Y177 115 kV line into 3T/4T position, and perform other associated substation work | 1225 | 2012-12-07 | No | Eversource | 2016-12-01
MA | 2015-12-01 | Greater Boston - North | Reconductor the F-158N 115kV line form Wakefield Jct - Maplewood and associated Maplewood Substation work | 1260 | 2015-05-01 | No | NGRID | 2015-12-01
MA | 2015-12-01 | NEEWS (Interstate Reliability Project) | Carpenter Hill Substation Relay Upgrade* | 1293 | NR | No | NGRID | 2015-12-01
MA | 2016-06-01 | Greater Boston - Western Suburbs*** | 69 kV Line reconductoring of W-23W Woodside-Northboro Rd | 1327 | 2015-05-01 | No | NGRID | 2016-05-01
MA | 2015-12-01 | Greater Boston - Western Suburbs*** | Refurbishment of 69 kV line X-24 Millbury-Northboro Rd | 1329 | NR | No | NGRID | 2015-12-01
MA | 2016-10-01 | Greater Boston - Western Suburbs*** | X-24/E-157W DCT Separation | 1330 | 2015-05-01 | No | NGRID | 2016-10-01
MA | 2017-12-01 | Greater Boston - Western Suburbs*** | Replace the existing 345/115 kV autotransformer with a higher rating transformer and 345 kV and 115 kV switchgear and breakers at Woburn | 1336 | No | No | Eversource | 2017-12-01
MA | 2016-12-01 | Greater Boston - Western Suburbs*** | Reconfigure Waltham Substation and one (1) 115kV breaker. Includes relocating terminations for PARs and 282-507 line. | 1337 | No | No | Eversource | 2016-12-01
MA | 2015-12-01 | Greater Boston - Western Suburbs*** | Upgrade 115 kV line 533-508 Lexington-Hartwell Ave by removing line clearance limitation and upgrading station equipment | 1339 | 2015-04-16 | NR | Eversource | 2015-12-01
MA | 2018-06-01 | Greater Boston - Central*** | Add a second Mystic 345/115 kV autotransformer and Mystic bus reconfiguration | 1352 | No | No | Eversource | 2018-06-01
MA | 2016-12-01 | Greater Boston - Central*** | Add one 115 kV breaker at K Street on the West bus | 1353 | No | No | Eversource | 2016-12-01
MA | 2017-12-01 | Greater Boston - Central*** | Add Mystic-Chelsea 115 kV cable | 1354 | No | No | Eversource | 2017-12-01
MA | 2018-12-01 | Greater Boston - Central*** | Split existing 110-522/240-510 DCT from Baker St. Station to Needham for a portion of the way and then install a new underground 115 kV line for the remainder of the way | 1355 | No | No | Eversource | 2018-12-01
MA | 2018-12-01 | Greater Boston - Central*** | Add a 2nd Mystic-Woburn 115 kV cable to create a bifurcated 211-514 Mystic-Woburn 115 kV circuit | 1356 | No | No | Eversource | 2018-12-01
MA | 2016-12-01 | Greater Boston - Central*** | Open up lines 329-510/511 and 250-516/517 at Mystic and Chatham respectively. Operate K Street as Normally Closed station | 1357 | No | NR | Eversource | 2016-12-01
MA | 2015-12-01 | Auburn Reliability Transmission System Upgrades | New Avon Substation A94 Tap | 1360 | 2010-02-10 | NR | NGRID | 2016-06-01
MA | 2015-12-01 | Greater Boston - Central*** | Separation of double Circuit Towers on Q-169/F-158N lines | 1363 | 2015-05-01 | No | NGRID | 2015-12-01
MA | 2016-12-01 |  | Tewksbury 22A 345 kV GIS Substation rebuild | 1395 | 2014-07-17 | No | NGRID | 2017-03-01
MA | 2016-06-01 | New Highland Park Substation Project | Terminal upgrades at Robinson Ave Substation (V-148S) | 1493 | 2013-01-18 | No | NGRID | 2017-06-01
MA | 2017-06-01 | Greater Boston - South*** | Construct a new 115 KV three breaker switching station in Sharon MA to segment the three 115 kV circuits that extend from West Walpole to Holbrook | 1516 | No | No | Eversource | 2017-06-01
MA | 2017-12-01 | Greater Boston - Central*** | Station upgrades to create a second normally closed 115 kV bus tie at Kingston Station and reconfigure the 345 kV switchyard | 1518 | No | No | Eversource | 2017-12-01
MA | 2016-12-01 | Greater Boston - Central*** | Relocate Chelsea capacitor bank 128-518 termination position | 1519 | 2015-05-01 | NR | Eversource | 2015-12-01
MA | 2017-05-01 | Greater Boston - Central*** | Equipment termination changes at North Cambridge Station to mitigate 115 kV stuck breaker 5 and 10 contingencies | 1520 | No | No | Eversource | 2017-05-01
MA | 2016-12-01 | Greater Boston - Central*** | Add a new 115 kV 54 MVAR capacitor bank at Newton Station | 1521 | No | NR | Eversource | 2016-10-01
MA | 2016-11-01 | Greater Boston - Central*** | Add a new 115 kV 36.7 MVAR capacitor bank at Sudbury Station | 1522 | No | NR | Eversource | 2016-11-01
MA | 2017-12-01 | Greater Boston - North*** | Reconductoring National Grid's portion of the Y-151 between Dracut Jct and Power Street (MA portion of the line) | 1527 | No | No | NGRID | 2017-12-01
MA | 2017-06-01 | Greater Boston - North*** | 115 kV Line Reconductoring of M-139 between Billerica Tap and Pinehurst and reconductoring of N-140 between Tewksbury and Pinehurst and associated work at Tewksbury | 1549 | 2015-05-01 | No | NGRID | 2017-05-01
MA | 2016-12-01 | Greater Boston - North*** | 115 kV Line reconductoring of the F-158S Maplewood - Everett | 1550 | 2015-05-01 | No | NGRID | 2016-12-01
MA | 2018-12-01 | Greater Boston - North*** | Terminal Work at Wakefield 345 kV substation for the new 345 kV cable between Woburn and Wakefield including the addition of a 160 MVAR variable shunt reactor | 1551 | No | No | NGRID | 2018-12-01
MA | 2018-12-01 | Greater Boston - North*** | Add a new 345 kV cable from Woburn substation to the Wakefield substation and terminal equipment at Woburn including a 160 MVAR 345 kV reactor | 1552 | No | No | Eversource | 2018-12-01
MA | 2016-12-01 | Greater Boston - Western Suburbs*** | Add a breaker in series with breaker 104 At Woburn 345 kV switchyard | 1553 | 2015-05-01 | No | Eversource | 2016-12-01
MA | 2016-11-01 | Greater Boston - Central*** | Add one 115 kV breaker at K street in series with the 29 breaker | 1554 | 2015-05-01 | NR | Eversource | 2016-11-01
MA | 2016-08-01 | Greater Boston - South*** | Add a new 345 kV breaker in series with the 104 breaker at Stoughton | 1558 | 2015-05-01 | NR | Eversource | 2016-08-01
MA | 2018-06-01 | Greater Boston - Stability*** | Upgrade the West Methuen115 kV station to BPS standards | 1636 | No | NR | NGRID | 2018-06-01
MA | 2017-05-01 | Greater Boston - North*** | Reconductor the National Grid portion of the M-139/211-503 and N-140/211-504 115 kV lines between Pinehurst – North Woburn tap | 1637 | 2015-05-01 | No | NGRID | 2017-05-01
MA | 2017-05-01 | Greater Boston - North*** | Reconductor the Eversource portion of the M-139/211-503 and N-140/211-504 115 kV lines between Pinehurst – North Woburn tap | 1640 | 2015-05-01 | NR | Eversource | 2017-05-01
MA | 2019-06-01 | Greater Boston - Stability*** | Upgrade the Edgar 115 kV station to BPS standards | 1641 | No | No | Eversource | 2016-10-01
MA | 2017-10-01 | Greater Boston - Stability*** | Upgrade the Dover 115 kV station to BPS standards | 1642 | No | No | Eversource | 2017-10-01
MA | 2019-06-01 | Greater Boston - Stability*** | Upgrade the Medway 115 kV station to BPS standards | 1644 | No | No | Eversource | 2019-06-01
MA | 2017-06-01 | Greater Boston - Western Suburbs*** | Add a new 115 kV breaker in series with breaker 5 at Framingham | 1647 | 2015-05-01 | NR | Eversource | 2017-06-01
MA |  | Greater Boston*** | Upgrade the East Cambridge 115kV station to BPS standards |  |  |  | Eversource | 2019-06-01
ME | 2017-01-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (255) between Larrabee Road and Middle Street (Lewiston Loop) | 1411 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2017-01-01
ME | 2017-01-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (256) between Middle Street and Lewiston Lower | 1413 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2017-01-01
ME | 2016-07-01 | Maine Power Reliability Program (MPRP) | Expand Norway 115 kV Substation interconnecting lines 61, 61A and 87 between stations Larabee Road, Hotel Road and Kimball Road (Lewiston Loop) | 1441 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2017-06-01
ME | 2017-01-01 | Maine Power Reliability Program (MPRP) | Expand Lewiston Lower 115 kV Substation interconnecting lines 256 and 202 between stations Middle Street and Crowleys (Lewiston Loop) | 1442 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2018-02-01
ME | 2017-01-01 | Maine Power Reliability Program (MPRP) | Add a new Middle Street 115/34/12 kV Substation interconnecting lines 255 and 256 between Lewiston Lower and new Larrabee Road (Lewiston Loop) | 1443 | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | CMP | 2017-04-01
ME | 2015-12-01 | Section 242 Rebuild | Rebuild entire length (1.1 mile) of transmission line Section 242 | 1513 | 2013-10-04 | NR | CMP | 2015-10-01
ME | 2018-12-01 | Greater Boston - Stability*** | Install a new +/- 200 MVAR STATCOM at Coopers Mills 345 kV substation | 1643 | No | No | CMP | 2019-05-01
NH | 2016-06-01 | LSP New Peaselee Substation and 115/34.5KV transformer | New 115 kV Peaslee Substation new 5.5 mile 115 kV line. New 115 kV capacitor banks. New 115 kV lines to Unitil substation and existing Kingston substation | 1183 | 2014-02-11 | No | Eversource | 2016-06-01
NH | 2017 | Greater Boston - North*** | Install a new 345 kV (3124) circuit between Scobie and Pelham NH (this is Eversource's portion of the new Scobie-Tewksbury circuit) | 1220 | No | No | Eversource | 2017-12-01
NH | 2016 | Western New Hampshire Solution | Amherst Substation - New 345 kV breaker and two 25 MVAR Capacitor Banks | 1269 | 2013-03-07 | No | Eversource | 2016-09-01
NH | 2016-12-01 | Western New Hampshire Solution | New 115 kV line from Fitzwilliam to Monadnock and associated substation work | 1270 | 2013-03-07 | No | Eversource | 2014-12-01
NH | 2016-12-01 | Central New Hampshire Solution | Saco Valley Substation - Add two 25 MVAR synchronous condenser devices | 1278 | 2013-03-07 | No | Eversource | 2015-10-01
NH | 2016-12-01 | Southern New Hampshire Solution | Eagle Substation Add: 345kV yard, (3) 345 kV circuit breakers, (4) 115kV circuit breakers, (1) 345/115 kV auto-transformer, (4) 26.6 MVAR 115 kV capacitor banks | 1301 | 2013-03-07 | No | Eversource | 2016-10-01
NH | 2015-11-01 | Southern New Hampshire Solution | Huse Rd Substation- Add:(2) 115 kV circuit breakers (associated with new circuit, Scobie Pond-Huse Rd) | 1303 | 2013-03-07 | No | Eversource | 2015-06-01
NH | 2015-12-01 | Southern New Hampshire Solution | New 115 kV overhead circuit, Scobie Pond-Huse Rd (W144) | 1304 | 2013-03-07 | No | Eversource | 2015-06-01
NH | 2017-12-01 | Seacoast New Hampshire Solution | Madbury Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Madbury-Portsmouth) | 1316 | 2013-03-07 | No | Eversource | 2016-12-01
NH | 2017-12-01 | Seacoast New Hampshire Solution | Portsmouth Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Madbury-Portsmouth) | 1317 | 2013-03-07 | No | Eversource | 2016-12-01
NH | 2017-12-01 | Seacoast New Hampshire Solution | New 115 kV overhead/submarine circuit, Madbury-Portsmouth | 1318 | 2013-03-07 | No | Eversource | 2016-12-01
NH | 2015-12-01 | Seacoast New Hampshire Solution | New 115 kV overhead circuit, Scobie Pond-Chester | 1319 | 2013-03-07 | No | Eversource | 2015-12-01
NH | 2015-12-01 | Seacoast New Hampshire Solution | Chester 115 kV Substation-Add: (5) 115 kV circuit breakers (associated with new circuit, Scobie Pond-Chester), | 1320 | 2013-03-07 | No | Eversource | 2015-12-01
NH | 2015-11-01 | Seacoast New Hampshire Solution | Schiller 115 kV Substation-Add: (3) 115 kV circuit breakers (6) 13.3 MVAR 115 kV capacitor banks | 1323 | 2013-03-07 | No | Eversource | 2015-12-01
NH | 2017 | Greater Boston - North*** | Reconductoring Eversource's portion of Y-151 between Pelham and Power Street | 1364 | No | No | Eversource | 2017-12-01
NH | 2017-12-01 | Greater Boston - North*** | Install new 345 kV (3124) circuit between Eversource border and NH/MA border (NH portion of National Grid's portion of new Scobie - Tewksbury line) | 1365 | No | No | NGRID | 2017-12-01
NH | 2017-12-01 | Greater Boston - North*** | Reconductoring National Grid's portion of the Y-151 between Dracut Jct and Power Street (NH portion of the line) | 1528 | No | No | NGRID | 2017-12-01
NH | 2016-06-01 | LSP-North Keene Substation Project | Replace four of the existing transformers at Keene substation with one 115/12.47 kV 30 MVA transformer;Construct a N. Keene Substation, loop in the L163 line with two 115 kV breakers, install one 115/12.47 kV 30 MVA transformer | 1660 | No | No | Eversource | 2016-06-01
NH | 2016-06-01 | LSP-Rimmon Substation Project | Rebuild Rimmon substation and add three 115 kV breakers, install a 2nd 115/34.5 kV transformer and two 115 kV 13.3 MVAR capaciters, connect the Rimmon substation to the J114 line; install a series 115 kV breaker at Greggs substation | 1661 | No | No | Eversource | 2016-06-01
RI | 2015-12-01 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | 794 | 9/24/2008 5/4/2012 | No | NGRID | 2015-12-01
RI | 2015-12-01 | NEEWS (Interstate Reliability Project) | New Sherman Road 345kV AIS Substation | 1233 | 2012-05-04 | No | NGRID | 2015-12-01
RI | 2015-12-01 | NEEWS (Interstate Reliability Project) | Re-conductor 345kV 328 line (West Farnum-Sherman Rd) | 1252 | 2012-05-04 | No | NGRID | 2015-12-01
RI | 2015-12-01 | NEEWS (Interstate Reliability Project) | New 345 kV (366) line MA/RI Border to West Farnum (4.8 miles) | 1298 | 9/24/2008 5/4/2012 | No | NGRID | 2015-12-01
RI | 2016-06-01 | New Highland Park Substation Project | Re-conductoring of J16 (Riverside - Highland Dr) | 1491 | 2013-01-18 | No | NGRID | 2017-06-01
RI | 2017-06-01 | Brayton Point Non-Price Retirement | Reconductor V-148N Line between Washington and Woonsocket Substations | 1623 | 2014-09-09 | No | NGRID | 2017-06-01
*As of October 2015 RSP Project Listing
**As noted in the memo sent to the Reliability Committee in Feburary 2014, the certification of these project components has only been accepted for CCP 2018-19 and beyond
***The certification of these project components has only been accepted for CCP 2019-20